## Sprint
|  |  |  | Week #1 (16 hrs / week) | [6 empty] | Week #2 (16 hrs / week) | [6 empty] | Week #3 (16 hrs / week) | [6 empty] | Week #4 (16 hrs / week) | [6 empty] | Week #5 (16 hrs / week) | [6 empty] | Week #6 (16 hrs / week) | [6 empty] | Week #7 (16 hrs / week) | [6 empty] | Week #8 (16 hrs / week) | [6 empty] | Week #9 (16 hrs / week) | [6 empty] | Week #10 (16 hrs / week)
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 16 x 10) | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11 | D12 | D13 | D14 | D15 | D16 | D17 | D18 | D19 | D20 | D21 | D22 | D23 | D24 | D25 | D26 | D27 | D28 | D29 | D30 | D31 | D32 | D33 | D34 | D35 | D36 | D37 | D38 | D39 | D40 | D41 | D42 | D43 | D44 | D45 | D46 | D47 | D48 | D49 | D50 | D51 | D52 | D53 | D54 | D55 | D56 | D57 | D58 | D59 | D60 | D61 | D62 | D63 | D64 | D65 | D66 | D67 | D68 | D69 | D70
 | time axis 2020-02-25 to 2020-05-04
|  |  |  | 160 | 158 | 156 | 154 | 150 | 146 | 144 | 144 | 142 | 140 | 139 | 138 | 134 | 128 | 128 | 128 | 126 | 122 | 117 | 114 | 112 | 112 | 112 | 108 | 106 | 102 | 100 | 96 | 96 | 95 | 91 | 89 | 85 | 83 | 80 | 80 | 80 | 79 | 75 | 73 | 68 | 64 | 64 | 64 | 60 | 58 | 52 | 51 | 48 | 48 | 47 | 46 | 44 | 37 | 33 | 32 | 32 | 32 | 30 | 26 | 22 | 18 | 16 | 16 | 14 | 13 | 9 | 4 | 2 | 0
|  |  | 160 | 2 | 2 | 2 | 4 | 4 | 2 | 0 | 2 | 2 | 1 | 1 | 4 | 6 | 0 | 0 | 2 | 4 | 5 | 3 | 2 | 0 | 0 | 4 | 2 | 4 | 2 | 4 | 0 | 1 | 4 | 2 | 4 | 2 | 3 | 0 | 0 | 1 | 4 | 2 | 5 | 4 | 0 | 0 | 4 | 2 | 6 | 1 | 3 | 0 | 1 | 1 | 2 | 7 | 4 | 1 | 0 | 0 | 2 | 4 | 4 | 4 | 2 | 0 | 2 | 1 | 4 | 5 | 2 | 2 | 0
Application Design | Application Design | Nachiket, Alaukika | 6 | 2020-02-25: 2; 2020-02-26: 2; 2020-02-27: 2
Database Design | Database Design | Sarthak, Amit | 6 | 2020-02-28: 2; 2020-02-29: 2; 2020-03-01: 2
Signup/ Login Portal | Admin Signup/Login (Frontend) | Alaukika | 4 | 2020-02-28: 2; 2020-02-29: 2
| Driver Signup/Login (Frontend) | Nachiket | 2 | bar: 2020-03-03 to 2020-03-04
| Admin Signup/Login (Backend) | Amit | 2 | bar: 2020-03-05 to 2020-03-06
| Driver Signup/Login (Backend) | Sarthak | 2 | bar: 2020-03-03 to 2020-03-04
Admin Module | Vehicle: Add/Edit/View/Delete (Frontend) | Alaukika | 10 | 2020-03-07: 4; 2020-03-11: 2; 2020-03-13: 2; 2020-03-18: 2
| Vehicle: Add/Edit/View/Delete (Backend) | Amit | 8 | 2020-03-08: 2; 2020-03-12: 2; 2020-03-13: 2; 2020-03-20: 2
| Admin Profile (Frontend) | Nachiket | 5 | 2020-03-08: 2; 2020-03-14: 3
| Admin Profile (Backend) | Sarthak | 5 | 2020-03-08: 2; 2020-03-12: 2; 2020-03-13: 1
| Location: Add/View/Delete (Frontend) | Nachiket | 10 | 2020-03-15: 1; 2020-03-20: 2; 2020-03-22: 2; 2020-03-25: 2; 2020-03-27: 2; 2020-04-01: 1
| Location: Add/View/Delete (Backend) | Amit | 8 | 2020-03-22: 2; 2020-03-26: 2; 2020-03-29: 2; 2020-04-02: 2
| VehicleType: Add/View/Delete(Frontend) | Alaukika | 10 | 2020-03-21: 2; 2020-03-25: 2; 2020-03-28: 2; 2020-04-03: 2; 2020-04-05: 2
| VehicleType: Add/View/Delete(Backend) | Sarthak | 8 | 2020-03-15: 1; 2020-03-18: 2; 2020-03-19: 2; 2020-03-24: 1; 2020-03-27: 2
| VehicleType Pricing: Add/Edit/Delete (Frontend) | Nachiket | 10 | 2020-04-04: 3; 2020-04-08: 2; 2020-04-10: 2; 2020-04-15: 1; 2020-04-17: 2
| VehicleType Pricing: Add/Edit/Delete (Backend) | Sarthak | 8 | 2020-03-29: 1; 2020-04-02: 2; 2020-04-05: 2; 2020-04-09: 2; 2020-04-11: 1
Driver Module | HomePage(Frontend) | Alaukika | 3 | 2020-05-01: 3
| HomePage(Backend) | Sarthak | 2 | bar: 2020-04-10; 2020-04-14
| NavBar(Frontend) | Sarthak | 4 | 2020-04-30: 2; 2020-05-03: 2
| NavBar(Backend) | Amit | 4 | 2020-04-04: 2; 2020-04-08: 2
| Driver Profile(Frontend) | Alaukika | 3 | 2020-04-10: 3
| Driver Profile(Backend) | Amit | 2 | 2020-04-12: 2
| Search/ browse vehicles (Search a rental location then view all vehicles in that location) | Alaukika | 5 | 2020-04-12: 1; 2020-04-16: 2; 2020-04-18: 2
| Search/ browse vehicles (Search for a vehicle across all locations) | Sarthak | 3 | 2020-04-17: 3
| Book Vehicle (Frontend) | Nachiket | 6 | 2020-04-19: 1; 2020-04-22: 2; 2020-04-25: 2; 2020-04-29: 1
| Book Vehicle (Backend) | Amit | 6 | 2020-04-17: 2; 2020-04-18: 2; 2020-04-23: 2
| Manage Upcoming/Ongoing/Past Booking (Frontend) | Alaukika,Nachiket | 10 | 2020-04-24: 2; 2020-04-26: 2; 2020-04-28: 2; 2020-05-01: 2; 2020-05-02: 2
| Manage Upcoming/Ongoing/Past Booking (Backend) | Sarthak, Amit | 8 | 2020-04-23: 2; 2020-04-24: 2; 2020-04-25: 2; 2020-04-30: 2
Team:
Nachiket | 4 hours / Week |  |  | 2020-03-16: Ideal Burndown
Alaukika | 4 hours / Week |  |  | 2020-03-16: Remaining Hrs (Total)
Sarthak | 4 hours / Week
Amit | 4 hours / Week
Total Available Hours During Sprint: | 160